## Sheet1
Task ID | Task Name | Description | Owner | Duration (days) | Depends On | Start Date | End Date
1 | Define architecture and connectivity scope | Identify on-prem and Azure data sources, workloads, and architecture boundaries | Data Architect | 3 |  | 2025-10-23 16:55 | 2025-10-25 16:55
2 | Validate ExpressRoute and private peering | Confirm ExpressRoute setup and private peering between on-prem and Azure | Network Engineer | 3 | 1 | 2025-10-26 16:55 | 2025-10-28 16:55
3 | Network and security assessment | Check firewalls, NSGs, DNS, and TLS for hybrid setup | Security Architect | 3 | 2 | 2025-10-29 16:55 | 2025-10-31 16:55
4 | Authentication and authorization planning | Plan Azure AD, hybrid identity, and access roles | Security Architect | 3 | 3 | 2025-11-01 16:55 | 2025-11-03 16:55
5 | Install on-prem data gateway | Deploy standard mode gateway and register with Power BI Service | Power BI Admin | 3 | 4 | 2025-11-04 16:55 | 2025-11-06 16:55
6 | Configure on-prem data sources | Connect SQL Server, Oracle, SAP etc. via gateway using ExpressRoute | Data Architect | 3 | 5 | 2025-11-07 16:55 | 2025-11-09 16:55
7 | Deploy VNet Data Gateway | Create Azure VNet Data Gateway and associate with correct VNet | Azure Engineer | 3 | 6 | 2025-11-10 16:55 | 2025-11-12 16:55
8 | Configure Azure data sources | Add Azure SQL, Synapse, Databricks using private endpoints | Azure Engineer | 3 | 7 | 2025-11-13 16:55 | 2025-11-15 16:55
9 | Combine data sources | Create composite models joining on-prem and Azure data | Data Architect | 4 | 8 | 2025-11-16 16:55 | 2025-11-19 16:55
10 | Apply data security | Implement RLS/OLS and Purview integration | Security Architect | 3 | 9 | 2025-11-20 16:55 | 2025-11-22 16:55
11 | Configure SSO and KCD | Implement Azure AD SSO and Kerberos constrained delegation | Security Architect | 4 | 10 | 2025-11-23 16:55 | 2025-11-26 16:55
12 | Map Power BI roles | Assign AAD groups to Power BI roles and apply access policies | Power BI Admin | 3 | 11 | 2025-11-27 16:55 | 2025-11-29 16:55
13 | Publish reports to Power BI Service | Deploy hybrid reports and configure refresh schedules | Power BI Admin | 3 | 12 | 2025-11-30 16:55 | 2025-12-02 16:55
14 | Validate on-prem access | Test report access via ExpressRoute and verify data privacy | Network Engineer | 2 | 13 | 2025-12-03 16:55 | 2025-12-04 16:55
15 | Enable monitoring and logging | Integrate gateway and Power BI logs with Azure Monitor | Azure Engineer | 3 | 14 | 2025-12-05 16:55 | 2025-12-07 16:55
16 | Implement governance controls | Enable auditing, Purview lineage, and compliance rules | Security Architect | 3 | 15 | 2025-12-08 16:55 | 2025-12-10 16:55
17 | Performance tuning | Optimize models, DirectQuery, and refresh strategy | Data Architect | 4 | 16 | 2025-12-11 16:55 | 2025-12-14 16:55
18 | Documentation and handover | Deliver runbooks, architecture diagrams, and training | Power BI Admin | 3 | 17 | 2025-12-15 16:55 | 2025-12-17 16:55